# SwipeLab Project Plan and Work Breakdown Structure

This document outlines the comprehensive project plan for the SwipeLab application, detailing the phases, work breakdown structure (WBS), assigned responsibilities, technical specifications, and key milestones, including the Alpha and Final Beta releases. This plan is based on the project proposal, application requirements document (ARD), and wireframes provided.

# I. Project Overview and Milestones

SwipeLab is a mobile application developed to accelerate the labeling of insect images for the STARdbi research project through gamified citizen science.

| Milestone | Target Date | Scope Focus |
| --- | --- | --- |
| Alpha Release | Date | Core Classification Loop (Login, Image Swipe, Points Update, Basic Data Submission) and essential Backend API integration. |
| Final Beta Release | Date | Full End-to-End System (All functionality: Gamification, Credibility Scoring, Research Dashboard, robust API integration, testing). |
| Final Delivery | Week 13 (per Proposal) | Final adjustments, documentation, and presentation. |

# II. Work Breakdown Structure (WBS) and Team Allocation

The project is divided into five core sections, each with specified technologies and responsibilities. The team consists of four members (Person 1, Person 2, Person 3, and Person 4) for work division.

## A. Frontend: Mobile Application (React Native/Expo)

Goal: Develop an intuitive, swipe-based mobile UI for image classification and gamification display.

Technology Stack: React Native with Expo, JavaScript/TypeScript.

| Task Category | Action Items | Deliverable | Assigned To | Status |
| --- | --- | --- | --- | --- |
| Setup & Core UI | Set up React Native/Expo project and Git repository. | Environment Ready | Person |  |
|  | Implement Login/Onboarding screens (UC-1). | Login/Auth Flow | Person |  |
|  | Implement Core Classification Screen (UC-2) with swipe gestures (Yes/No/IDK). | Classification UI | Person |  |
|  | Implement Offline Classification Queue and Sync (3.1.7.1). | Offline Capability | Person |  |
| Gamification UI | Develop Progress/Points screen to display stats (3.1.4.1). | Personal Stats View | Person |  |
|  | Implement Leaderboard screen display (3.1.3.3) and Streak tracking (3.1.3.4). | Leaderboard View | Person |  |
|  | Implement Badge/Achievement display logic (3.1.3.2). | Achievements View | Person |  |
| Testing | Implement Unit and Integration tests for Frontend components. | Test Coverage | Person |  |

## B. Backend: API Server (Java Spring Boot/PostgreSQL)

Goal: Create a scalable, secure REST API to manage users, data, scoring, and coordinate with the external STARdbi API.

Technology Stack: Java Spring Boot, PostgreSQL, Spring Security (OAuth2/JWT).

| Task Category | Action Items | Deliverable | Assigned To | Status |
| --- | --- | --- | --- | --- |
| Setup & Auth | Set up Spring Boot project structure and PostgreSQL database schema. | Backend Environment | Person |  |
|  | Implement Google/OAuth2 authentication and JWT token management (3.2.1.1). | Secure Auth API | Person |  |
|  | Implement Role-Based Access Control (RBAC) (3.2.1.3) for Volunteer/Researcher/Admin. | User Roles Logic | Person |  |
| Core Logic | Implement endpoints for Classification Recording and Task Distribution (3.2.2). | Data Submission API | Person |  |
|  | Implement Credibility Score Calculation logic (3.2.3.1) based on Trap Images. | Credibility Service | Person |  |
|  | Implement Consensus Calculation (3.2.4.1) with credibility weighting. | Consensus Service | Person |  |
| Gamification Logic | Implement Point Allocation and Streak/Reward logic (3.2.5.1). | Points/Reward Service | Person |  |
|  | Implement Leaderboard generation service (3.2.5.3). | Leaderboard Logic | Person |  |

## C. Data & API Integration (STARdbi)

Goal: Establish secure, reliable communication with the customer's dataset API for image fetching and submission.

Technology Stack: Java Spring Boot (REST Client), Secure Protocols (HTTPS/Token-based Auth).

| Task Category | Action Items | Deliverable | Assigned To | Status |
| --- | --- | --- | --- | --- |
| External API | Define API Spec and mock data for STARdbi dataset API endpoints (1.5.2 Input). | Mock API Client | Person |  |
|  | Implement secure API client for fetching image batches (Image ID, Metadata). | Image Fetching Client | Person |  |
|  | Implement secure API client for submitting classification labels (Auditability requirement). | Label Submission Client | Person |  |
| Quality Control | Implement Fraud Detection/Anti-Bot logic (3.2.3.3) (e.g., response time checks). | Fraud Detection Logic | Person |  |
| Data Export | Implement Dataset Export functionality (3.2.6.1) (CSV/JSON generation). | Data Export API | Person |  |

## D. Research Dashboard (Web/Admin Panel)

Goal: Develop a web interface for researchers to manage tasks, monitor progress, and export data. (Referenced in [3] wireframes.pptx and ARD 3.3).

Technology Stack: Web Framework (e.g., React or simple server-side rendering for minimal effort), REST API interaction.

| Task Category | Action Items | Deliverable | Assigned To | Status |
| --- | --- | --- | --- | --- |
| Dashboard Core | Implement Researcher Login and Authentication (3.3.1). | Dashboard Auth | Person |  |
|  | Implement Progress Monitoring/Task Dashboard View (3.3.4.1). | Task Overview UI | Person |  |
| Management Tools | Implement Trap Picture Definition/Management (UC-5) interface. | QC Management UI | Person |  |
|  | Implement Task Creation Wizard (UC-6) with Reference Picture Upload (3.3.2.1-2). | Task Creation UI | Person |  |
|  | Implement User Performance Analytics and Moderation tools (3.3.4.3, 3.3.6.2). | User Management UI | Person |  |
|  | Implement Data Export configuration and trigger (UC-4) (3.3.5.1). | Export Data UI | Person |  |

## E. Documentation, Testing, and Deployment

Goal: Ensure code quality, system stability, and comprehensive documentation for future maintenance.

| Task Category | Action Items | Deliverable | Assigned To | Status |
| --- | --- | --- | --- | --- |
| Testing | Write Unit tests for all Backend services (3.2). | Unit Test Coverage | All |  |
|  | Perform Integration Testing: Frontend to Backend, Backend to STARdbi API. | Integration Test Suite | All |  |
|  | Plan and execute Performance/Load Testing (4.1.1). | Performance Report | Person |  |
| Deployment | Implement CI/CD pipeline using GitHub Actions (per Proposal). | Automated Deployment | Person |  |
|  | Containerize Backend (Docker) for AWS/GCP deployment. | Docker Images | Person |  |
| Documentation | Maintain a project wiki/documentation for API endpoints and data schemas. | Project Wiki | All |  |
|  | Prepare for Pilot User Evaluation (UAT) in Week 12. | UAT Plan and Report | Person |  |

# III. Team Work Allocation and Division of Labor

The four team members will divide the work based on the project’s major components (Frontend, Backend, Integration, and Dashboard/Testing).

| Team Member | Primary Focus Area (Approx. 60% of Time) | Secondary Focus Area (Approx. 40% of Time) |
| --- | --- | --- |
| Person (P1) | Backend Core & Security (Auth, JWT, RBAC, Database) | Data Integration (Image Fetching Client) |
| Person (P2) | Frontend Core & UX (Classification UI, Swipe Logic, Offline Mode) | Frontend Gamification UI (Stats, Badges) |
| Person (P3) | Data Logic & Integration (Credibility, Consensus, Fraud, STARdbi Submission) | Research Dashboard (Export, Analytics Logic) |
| Person (P4) | Research Dashboard & Testing (Dashboard UI, Task/QC Mgmt, System Testing) | Deployment/CI/CD, Frontend Gamification UI (Leaderboards) |

# IV. Project Timeline and Key Phases

The timeline follows the structure provided in the project proposal, with a focus on meeting the Alpha and Beta release dates.

| Phase | Duration | Weeks (Approximate) | Deliverables & Focus |
| --- | --- | --- | --- |
| Phase 0: Planning & Setup | 1 Week | Current - Week 1 | Finalize WBS, set up environments (Git, React Native, Spring Boot), define API contract with mocked data. |
| Phase 1: Alpha Core Development | 3 Weeks | Week 2 - Date | Implement Core Auth, Classification UI/Swipe Logic, and Basic Data Submission to mock/staging API. Minimal points/stats displayed. |
| Phase 2: Beta Feature Implementation | 5 Weeks | Date - Date | Implement Credibility Scoring, Consensus Logic, Full Gamification, Research Dashboard Core (Task/QC Mgmt, Analytics), and Real STARdbi API Integration. |
| Phase 3: Testing & Polish | 2 Weeks | Date - //Date | Full system testing, performance optimization, bug fixes, data export validation. |
| Phase 4: UAT & Final Delivery | 2 Weeks | Date - Week 13 | Conduct User Acceptance Testing (UAT) with researchers, implement final adjustments, prepare documentation and presentation. |

# V. Technical Specifications and Workflow

## A. Technical Stack Summary

| Component | Technology | Rationale (Per Proposal/ARD) |
| --- | --- | --- |
| Frontend | React Native with Expo | Cross-platform (iOS/Android), mobile-first, fast iteration. |
| Backend | Java Spring Boot | Robust, scalable, and secure REST API framework. |
| Database | PostgreSQL | Relational DB for user data, labels, and statistics. |
| Authentication | Google Sign-In (OAuth2) + JWT | Secure, standard method for user authentication. |
| Version Control | Git + GitHub | Standard industry practice. |
| Deployment | Docker + GitHub Actions (CI/CD) | Automated testing and deployment. |

## B. Development Workflow

- Branching Strategy: Use a modified Git-Flow: main (Production), staging (Beta/UAT), and feature branches (feature/name, bugfix/name).

- Feature Development: Developers work on dedicated feature branches.

- Code Review: All feature branches must be reviewed and pass automated tests before merging into staging.

- Integration Testing: Merges to staging trigger integration tests against the test/staging environment.

- Release: Once staging is stable, it is merged into main for major releases (Alpha, Beta, Final).

## C. GitHub Repository

Link: FileSwipeLab GitHub Repository Link

## D. Documentation and API Specification

- Maintain a live API Specification (e.g., using Swagger/OpenAPI) that documents all REST endpoints, request/response schemas, and error codes.

- The Backend and Frontend teams must align on API contracts before starting feature implementation to avoid integration risks.

- API Link: FileSwipeLab API Documentation/Swagger Link

## E. Alpha Release Deliverables (Target: Date)

The Alpha release focuses on the minimal viable product for the core user loop.

- Authentication: Volunteer login via Google/Email.

- Classification: Functional swipe interface (Yes/No/IDK) with next image retrieval.

- Data Submission: Classification data is recorded on the backend (including response time/metadata).

- Basic Progress: Display of total points and classification count on the profile screen.

- Basic Stability: Initial unit and integration tests passed.

## F. Final Beta Release Deliverables (Target: Date)

The Final Beta release includes all functional and non-functional requirements.

- Full Frontend: All screens (Classification, Stats, Leaderboard, Badges) complete and functional.

- Full Backend Logic: Credibility Scoring, Consensus Calculation, Fraud Detection, and Leaderboard ranking fully implemented.

- Dashboard: Researcher dashboard fully functional (Task/Gold/User/Export Management).

- API Integration: Live integration with the STARdbi dataset API.

- Security/Stability: All Non-Functional Requirements met (e.g., 99% uptime goal, HTTPS, password hashing).

- UAT Ready: System ready for testing by external users/researchers.

# VI. Research Dashboard Wireframe Review and Implementation Plan

The Research Dashboard is a key component to satisfy the Researchers' requirements (UC-4, UC-5, UC-6). The wireframes ([3] wireframes.pptx) show the required screens:

| Wireframe Screen | Corresponding ARD/Proposal Requirement | Implementation Notes |
| --- | --- | --- |
| Manager Dashboard Homepage | Task Creation (UC-6), System Overview (3.3.4.1) | Must include links to Experiments (Tasks), Taxonomies, and Gold Images. |
| Experiments Tab | Task Management (3.3.2.1) | List of tasks (e.g., "A Very Long Name"), showing location and placement/removal dates. |
| Gold Images Tab | Trap Picture Definition (UC-5, 3.3.3.1) | Allows researchers to upload images and assign expert classification for quality control. |
| Users Tab | User Management/Analytics (3.3.6.1, 3.3.4.3) | Displays anonymized users and their credibility scores. Must allow admin moderation. |
| Add Experiment Tab | New Task/Experiment Configuration (UC-6) | Form to define task name, classification question, and associate datasets. |
| Add Gold Image Tab | Gold Image Upload (3.3.3.1) | Interface for uploading image and defining its correct taxonomy/classification. |

Action Item: Person (P4, Dashboard Owner) must create low-fidelity mockups for data visualization charts (progress, consensus distribution, user stats) not fully detailed in the provided wireframes.

| Action Item | Assigned To | Status |
| --- | --- | --- |
| Create mockups for data analytics views in Dashboard. | Person |  |
| Implement API integration for Dashboard data visualization endpoints. | Person |  |
| Finalize export configuration form and file generation handler. | Person |  |

# Comprehensive Project Task Checklist

The following is a consolidated list of all action items from the Work Breakdown Structure, structured as a checklist for tracking progress.

## A. Frontend: Mobile Application (React Native/Expo)

- Set up React Native/Expo project and Git repository (P?).

- Implement Login/Onboarding screens (UC-1) (P?).

- Implement Core Classification Screen (UC-2) with swipe gestures (Yes/No/IDK) (P2).

- Implement Offline Classification Queue and Sync (3.1.7.1) (P2).

- Develop Progress/Points screen to display stats (3.1.4.1) (P2).

- Implement Leaderboard screen display (3.1.3.3) and Streak tracking (3.1.3.4) (P4).

- Implement Badge/Achievement display logic (3.1.3.2) (P2).

- Implement Unit and Integration tests for Frontend components (P?).

## B. Backend: API Server (Java Spring Boot/PostgreSQL)

- Set up Spring Boot project structure and PostgreSQL database schema (P1).

- Implement Google/OAuth2 authentication and JWT token management (3.2.1.1) (P1).

- Implement Role-Based Access Control (RBAC) (3.2.1.3) for Volunteer/Researcher/Admin (P1).

- Implement endpoints for Classification Recording and Task Distribution (3.2.2) (P1).

- Implement Credibility Score Calculation logic (3.2.3.1) based on Trap Images (P3).

- Implement Consensus Calculation (3.2.4.1) with credibility weighting (P3).

- Implement Point Allocation and Streak/Reward logic (3.2.5.1) (P3).

- Implement Leaderboard generation service (3.2.5.3) (P3).

## C. Data & API Integration (STARdbi)

- Define API Spec and mock data for STARdbi dataset API endpoints (1.5.2 Input) (P3).

- Implement secure API client for fetching image batches (Image ID, Metadata) (P1).

- Implement secure API client for submitting classification labels (Auditability requirement) (P3).

- Implement Fraud Detection/Anti-Bot logic (3.2.3.3) (e.g., response time checks) (P3).

- Implement Dataset Export functionality (3.2.6.1) (CSV/JSON generation) (P3).

## D. Research Dashboard (Web/Admin Panel)

- Implement Researcher Login and Authentication (3.3.1) (P4).

- Implement Progress Monitoring/Task Dashboard View (3.3.4.1) (P4).

- Implement Trap Picture Definition/Management (UC-5) interface (P4).

- Implement Task Creation Wizard (UC-6) with Reference Picture Upload (3.3.2.1-2) (P4).

- Implement User Performance Analytics and Moderation tools (3.3.4.3, 3.3.6.2) (P4).

- Implement Data Export configuration and trigger (UC-4) (3.3.5.1) (P4).

## E. Documentation, Testing, and Deployment

- Write Unit tests for all Backend services (3.2) (All).

- Perform Integration Testing: Frontend to Backend, Backend to STARdbi API (All).

- Plan and execute Performance/Load Testing (4.1.1) (P4).

- Implement CI/CD pipeline using GitHub Actions (per Proposal) (P4).

- Containerize Backend (Docker) for AWS/GCP deployment (P4).

- Maintain a project wiki/documentation for API endpoints and data schemas (All).

- Prepare for Pilot User Evaluation (UAT) in Week 12 (P?).

## VI. Research Dashboard Implementation Plan

- Create mockups for data analytics views in Dashboard (P4).

- Implement API integration for Dashboard data visualization endpoints (P3).

- Finalize export configuration form and file generation handler (P4).